# Full Delivery Plan

## Overall timeline

The TRD already structures the project into 4 major phases across 12 months:

- Phase 0: Discovery + Planning + Setup → 2 weeks

- Phase 1: MVP → Months 1–3

- Phase 2: Growth / Public Beta → Months 4–6

- Phase 3: Monetization → Months 7–9

- Phase 4: Scale & Intelligence → Months 10–12

To make this practical, I would run it as:

- Weeks 1–2: Pre-build planning and architecture setup

- Weeks 3–14: MVP execution

- Weeks 15–26: Search scale-up, discovery, moderation, beta

- Weeks 27–38: Payments, subscriptions, boosts, seller monetization

- Weeks 39–52: AI pricing, KYC, escrow, multilingual, advanced trust features

# Phase 0 — Discovery, architecture, team alignment, foundations

## Duration

2 weeks

## Goal

Convert the TRD into execution-ready engineering workstreams before feature development begins. The document explicitly says competitor and technical study should happen before production coding, and the system is meant to be delivered as a multi-platform product with shared backend standards.

## Detailed tasks

### 1. Product and benchmark analysis

Deadline: End of Week 1

- Study Dubizzle / OLX flows for listings, motors, property verification

- Study Bayut / Property Finder map-based search and verification patterns

- Study Avito, OfferUp, Wallapop, Craigslist, Gumtree for UX, trust, monetization, and performance trade-offs

- Extract:

  - must-have UX patterns

  - search/filter expectations

  - verification expectations

  - monetization patterns

  - what to avoid over-engineering in MVP

### 2. Architecture decision record

Deadline: End of Week 1

- Finalize service list from TRD:

  - auth-service

  - user-service

  - listing-service

  - search-service

  - chat-service

  - media-service

  - payment-service

  - boost-service

  - notification-service

  - moderation-service

  - analytics-service

  - api-gateway

- Decide initial deployment approach:

  - MVP can start with fewer deployable services but still maintain clear service boundaries

- Confirm stack:

  - Next.js 14+

  - Flutter 3.x

  - Node.js 20 + TypeScript + Fastify

  - PostgreSQL 16+

  - Redis 7+

  - Elasticsearch 8.x

  - Kafka/Debezium in later phase

  - Kong Gateway

  - S3/R2 + Cloudinary

  - Socket.IO

  - SendGrid, Twilio, FCM, Stripe, Checkout.com, Onfido/Jumio, Rekognition, Sentry, Mixpanel/PostHog

### 3. Repository and environment strategy

Deadline: Mid Week 2

- Create repo structure:

  - web-app

  - mobile-app

  - backend-services

  - infra / helm / deployment

  - shared contracts / API schemas

- Create dev/staging/prod environment strategy

- Create secrets handling plan

- Setup branch strategy, PR templates, code owners, review rules

### 4. Data model and API contract definition

Deadline: End of Week 2

- Finalize PostgreSQL schema:

  - users

  - listings

  - categories

  - listing_images

  - conversations

  - messages

  - boosts

  - transactions

  - reports

- Define JSONB category schema strategy

- Define base API response envelope:

  - { data, meta, errors }

- Define cursor pagination standard

- Define auth conventions and token flows

- Write OpenAPI specs / endpoint contracts for Phase 1 services

### 5. Delivery management setup

Deadline: End of Week 2

- Break all work into epics and sprint tickets

- Define sprint cadence: 2-week sprints

- Define release gates per phase

- Create QA checklist, DoD checklist, security checklist, performance checklist

## Deliverables by end of Phase 0

- Signed architecture document

- Repo structure created

- Environment strategy approved

- Service responsibilities locked

- API contracts drafted

- Sprint backlog ready

# Phase 1 — MVP

## Duration

12 weeks total
Approx: Weeks 3–14

## Goal

Launch a working marketplace where users can register, create listings with photos, browse/search, view listing details, and chat with sellers on web and mobile. This matches the TRD MVP definition.

## Sprint 1 — Infrastructure + auth foundation

### Duration

Weeks 3–4

### Tasks

#### Backend foundation

- Setup Fastify service templates

- Setup shared logging, validation, error handling

- Setup PostgreSQL and Redis in dev/staging

- Setup Docker for all services

- Setup basic Kubernetes manifests / Helm charts

- Setup Kong / gateway routing

- Setup CI/CD:

  - build

  - test

  - Docker image push

  - deploy to staging

#### Auth service

- Email/password registration

- Email verification flow

- OTP flow for phone verification

- Google OAuth

- JWT access token issuance

- Refresh token storage in Redis

- Refresh token rotation

- Role model setup:

  - user

  - business

  - moderator

  - admin

#### Security baseline

- Joi or Zod validation

- Rate limiting at gateway

- TLS-only environments

- secret management for dev/staging

- Dependabot/Snyk

- initial CORS whitelist

#### Frontend/mobile bootstrap

- Next.js app shell

- Flutter clean architecture setup

- Dio ApiService with auth interceptors

- Route guards

- auth screens scaffolding

### Exit criteria

- Users can sign up and log in on web/mobile

- Refresh token flow works

- OTP can be verified

- CI/CD deploys to staging

## Sprint 2 — User profiles + categories + admin basics

### Duration

Weeks 5–6

### Tasks

#### User service

- Profile CRUD

- avatar upload

- public profile API

- profile edit on web/mobile

- verification status fields

- reputation score placeholder support

#### Category system

- categories table

- category tree seed

- schema_definition JSONB design

- API for category tree

- API for category schema

- admin category CRUD UI

- cache category tree in Redis

#### Admin base

- admin login / RBAC

- category management screen

- basic user management stub

- listing moderation queue placeholder

#### Mobile/web

- category navigation on web

- category chip/list UI on mobile

- public seller profile widget stub

### Exit criteria

- Categories can be managed from admin

- Frontends can consume category tree dynamically

- Public profile endpoint is live

## Sprint 3 — Listing creation and management

### Duration

Weeks 7–8

### Tasks

#### Listing service core

- Create listing endpoint

- Edit listing endpoint

- Delete listing endpoint

- Draft support

- Listing status lifecycle:

  - Draft

  - Active

  - Expired

  - Sold

  - Removed

- JSONB validation against category schema

- expiry rules by category

- ownership checks for update/delete

#### Media service MVP

- presigned upload flow

- upload up to 10 images for MVP

- image metadata storage

- primary image support

- image ordering support

- MIME validation

- file scanning hook stub

#### Web listing posting flow

- multi-step wizard:

  - category

  - dynamic attributes

  - photos

  - price + location

  - review

  - publish

- draft autosave to localStorage

- backend draft sync

#### Mobile listing posting flow

- Flutter step-based posting flow

- gallery/camera image picker

- image compression

- upload retry support

- draft recovery

### Exit criteria

- User can create, edit, save draft, publish, and manage listings

- Dynamic forms work from category schema

- Images upload successfully

## Sprint 4 — Search MVP + listing detail

### Duration

Weeks 9–10

### Tasks

#### MVP search

The TRD says PostgreSQL full-text search can be used in MVP, with Elasticsearch migration planned for Phase 2.

- implement PostgreSQL full-text search

- search endpoint with pagination

- category filter

- basic sort:

  - newest

  - price asc

  - price desc

- location filter stub

- status=active enforcement

#### Listing detail

- listing detail API

- image gallery

- seller widget

- report listing modal

- view count via Redis approximate store

- related listings fallback logic

- save/favourite toggle

#### Web/mobile screens

- search results page

- listing detail page

- home feed

- saved items

- my listings screen

### Exit criteria

- Search works across active listings

- listing detail is production-usable

- favourites and my listings function end-to-end

## Sprint 5 — Chat and notifications MVP

### Duration

Weeks 11–12

### Tasks

#### Chat service

- create conversation

- conversation list

- message storage

- WebSocket auth

- text messages

- unread badge counts

- read receipts

- typing indicators

- conversation update event

- listing-card shared message type

#### Notification MVP

- in-app notifications table

- FCM setup for Android

- APNs bridge through FCM for iOS

- send push on new message when disconnected

- email templates for welcome and listing publish

- SMS for OTP only

#### UI

- web inbox

- mobile inbox

- chat thread

- badge counts

- deep-link from listing to chat

### Exit criteria

- Buyer can start chat from listing

- Seller receives messages in real time

- push fallback works

## Sprint 6 — Admin moderation + hardening + MVP release

### Duration

Weeks 13–14

### Tasks

#### Admin MVP

- basic moderation queue

- listing approve/reject/remove

- user search by phone/email

- manual ban/unban

- report list view

#### Security hardening

- ownership checks audit

- SQL injection review

- input validation audit

- file upload validation audit

- refresh rotation test

- logging and monitoring alerts

#### Quality

- unit tests to minimum threshold

- integration tests for Phase 1 APIs

- smoke tests for web/mobile

- load test critical endpoints

- bug fixing and release prep

### Phase 1 deadline

End of Week 14

### Phase 1 release gate

Before Phase 1 closes:

- registration works

- listing posting works

- search works

- chat works

- admin can moderate

- web + Android + iOS builds usable

- CI/CD stable

- performance acceptable for MVP

# Phase 2 — Growth / Public Beta

## Duration

12 weeks
Approx: Weeks 15–26

## Goal

Replace MVP search with Elasticsearch, add geo features, improve discovery, add moderation intelligence, push notifications, and public beta readiness. This aligns directly with the TRD Phase 2 scope.

## Sprint 7 — Elasticsearch architecture

### Duration

Weeks 15–16

### Tasks

- provision Elasticsearch + Kibana

- define listings_v1 mapping

- define users_v1 mapping

- create indexing pipeline

- build search-service

- write ES query builder

- build autocomplete suggest API

- create reindex job for existing listings

- design alias/versioning strategy for indices

### Exit criteria

- ES indices created

- listings searchable from ES in staging

## Sprint 8 — CDC pipeline + search migration

### Duration

Weeks 17–18

### Tasks

- setup Kafka

- setup Debezium connector

- publish listings change events

- consume events in search-service

- upsert/delete into Elasticsearch

- ensure replication lag target

- cut over listing search endpoint from PostgreSQL to ES

- verify status filters, faceted filters, sorting, ranking

### Exit criteria

- Search is fully ES-backed

- CDC replication stable

## Sprint 9 — Dynamic filters + saved search + map discovery

### Duration

Weeks 19–20

### Tasks

- dynamic filter rendering from category schema

- advanced filtering:

  - price range

  - condition

  - date

  - category-specific fields

- geo_distance filters

- geo bounding box support

- map clustering

- web map view

- mobile map view

- save search feature

- saved search alert preferences

### Exit criteria

- Users can search with advanced filters and map mode

- saved searches persist properly

## Sprint 10 — Media optimization + performance caching

### Duration

Weeks 21–22

### Tasks

- Cloudinary integration

- WebP thumbnails

- lazy loading

- media transformation rules

- optimize mobile upload flow for 10 photos under target timing

- Redis caching for:

  - category tree

  - search result hashes

  - view counts

  - session/token stores

- optimize web LCP and mobile cold start

### Exit criteria

- image delivery optimized

- caches reduce repeated query load

- performance metrics improve materially

## Sprint 11 — AI moderation v1

### Duration

Weeks 23–24

### Tasks

- moderation-service foundation

- image scan integration with Rekognition / Vision API

- text fraud detection v1

- anomaly rules:

  - suspicious pricing

  - external URL/phone bypass

  - scam phrase patterns

- moderation score thresholds

- human review queue enrichment

- notifications for approve/reject

- moderation dashboard improvements

### Exit criteria

- Listings are scored asynchronously

- risky listings are held or rejected properly

## Sprint 12 — Push, beta stabilization, Phase 2 close

### Duration

Weeks 25–26

### Tasks

- complete FCM/APNs flows

- grouped notifications center

- notification settings screen

- beta bug fixing

- OWASP review before beta

- k6 testing

- Lighthouse improvement

- Playwright and mobile E2E introduction

- staging-to-beta release checklist

### Phase 2 deadline

End of Week 26

### Phase 2 release gate

- ES search in production

- geo search and maps work

- advanced filters work

- image CDN live

- saved searches active

- push notifications active

- AI moderation v1 running

- public beta ready

# Phase 3 — Monetization

## Duration

12 weeks
Approx: Weeks 27–38

## Goal

Turn on revenue through pay-to-post, boosts, subscriptions, lead credits, seller analytics, and WhatsApp lead alerts. This is exactly the TRD Phase 3 objective.

## Sprint 13 — Payments foundation

### Duration

Weeks 27–28

### Tasks

- payment-service foundation

- Stripe integration

- Checkout.com integration

- payment session API

- transaction recording

- webhook handlers

- failed/successful payment lifecycle

- invoice/receipt email templates

- payment retry UX

### Exit criteria

- payment checkout works end-to-end

## Sprint 14 — Pay-to-post and subscription plans

### Duration

Weeks 29–30

### Tasks

- gated categories for paid posting

- checkout at end of listing wizard

- posting access control based on payment result

- subscription plan models

- Pro and Business plan rules

- Stripe Billing setup

- subscription lifecycle:

  - activate

  - renew

  - cancel

  - expire

- plan badge in profile/dashboard

- listing quota enforcement

### Exit criteria

- paid posting works

- subscriptions work

## Sprint 15 — Boost engine

### Duration

Weeks 31–32

### Tasks

- boosts table workflows

- boost-service

- boost types:

  - Bump

  - Highlight

  - Top Ad

- active boost cron

- boost_rank_score updates in Elasticsearch

- queueing logic for Top Ad slots

- purchase UX

- boost status in seller dashboard

- boost expiry reminders

### Exit criteria

- listings can be boosted and reflected in search ranking

## Sprint 16 — Lead credits + seller analytics

### Duration

Weeks 33–34

### Tasks

- lead credit wallet

- purchase credits

- consume credits to reveal contact

- balance and transaction history

- analytics-service event model

- seller dashboard:

  - views

  - clicks

  - chat requests

  - favourites

  - boost performance

- Mixpanel/PostHog event mapping

- admin revenue reporting

### Exit criteria

- credit system works

- seller analytics useful and reliable

## Sprint 17 — WhatsApp lead alerts + featured business profiles

### Duration

Weeks 35–36

### Tasks

- WhatsApp Business integration

- approved templates for lead alerts

- seller lead notification rules

- featured agent/store profile model

- branded business profile pages

- category pinning logic

- business verification dependencies mapped

### Exit criteria

- sellers can receive lead alerts

- branded business profiles visible

## Sprint 18 — Monetization hardening + release

### Duration

Weeks 37–38

### Tasks

- payment reconciliation tests

- fraud review around purchases

- subscription edge-case testing

- webhook retry and idempotency audit

- performance testing under paid flows

- external penetration test before monetization launch

- release prep

### Phase 3 deadline

End of Week 38

### Phase 3 release gate

- pay-to-post active

- boosts active

- subscriptions active

- lead credits active

- analytics active

- WhatsApp alerts active

- pen test completed

# Phase 4 — Scale & Intelligence

## Duration

14 weeks
Approx: Weeks 39–52

## Goal

Add the advanced intelligence and trust layers: AI price suggestion, KYC Level 2, escrow, virtual tours, multilingual support, and optional logistics. This matches the TRD Phase 4 scope.

## Sprint 19 — AI price estimator

### Duration

Weeks 39–40

### Tasks

- collect historical listing/trade data requirements

- define training dataset format

- build regression model baseline

- evaluation metrics and confidence range

- pricing-service API

- cache strategy for price estimates

- web/mobile inline price suggestion UI

- fallback when insufficient data

### Exit criteria

- pricing API returns usable range suggestions

## Sprint 20 — KYC Level 2 and business verification

### Duration

Weeks 41–42

### Tasks

- Onfido/Jumio integration

- national ID/passport upload flow

- liveness check flow

- review queue fallback

- verification state machine

- verified badges in UI

- enforcement rules for motors and real estate

- business document upload and ops review

- audit logging

### Exit criteria

- ID verification flow works end-to-end

## Sprint 21 — Escrow wallet foundation

### Duration

Weeks 43–44

### Tasks

- Stripe Connect setup

- escrow account flows

- Buy Now flow

- hold funds logic

- release after 48h logic

- dispute initiation flow

- admin dispute resolution tooling

- payout request model

- withdrawal handling

- fee deduction rules

### Exit criteria

- controlled escrow test transactions can run end-to-end

## Sprint 22 — Virtual tours + multilingual support

### Duration

Weeks 45–46

### Tasks

- 360 tour embed support

- listing field support for motors and real estate

- mobile/web rendering

- Arabic RTL implementation

- Urdu and Hindi language packs

- i18n architecture in web/mobile

- locale-aware formatting

- content translation support for categories and UI labels

### Exit criteria

- product supports multilingual UI and tour embeds

## Sprint 23 — Optional logistics + advanced trust scoring

### Duration

Weeks 47–48

### Tasks

- logistics integration feasibility

- shipping provider API spike

- reputation score engine completion

- star rating mapping

- trust score inputs:

  - completed sales

  - reviews

  - account age

  - verification

  - removals/reports/chargebacks

- risk and fraud dashboards

- trust score display on profiles/listings

### Exit criteria

- reputation system fully reflected in product

## Sprint 24 — Final scale, audit, launch readiness

### Duration

Weeks 49–52

### Tasks

- full system load testing

- latency optimization

- index optimization

- DB query optimization

- app store production preparation

- compliance review

- disaster recovery runbooks

- observability dashboards complete

- incident response playbooks

- final UAT

- final security audit

- launch readiness review

### Phase 4 deadline

End of Week 52

### Final release gate

- AI pricing live

- KYC Level 2 live

- escrow live

- tours live

- multilingual support live

- trust score live

- scale/performance/security targets met

# Cross-functional workstreams that run across all phases

## 1. QA and testing

The TRD requires unit, integration, and later E2E coverage, plus load testing.

### Continuous tasks

- unit tests per service

- API integration tests

- contract testing between frontend/mobile and backend

- regression suite per sprint

- Playwright for web from Phase 2

- Patrol/Maestro for mobile from Phase 2

- load tests with k6 before each phase close

## 2. DevOps and observability

### Continuous tasks

- CI/CD improvements

- deployment rollback strategy

- monitoring dashboards

- alerting thresholds

- structured logs

- distributed tracing

- cost optimization

- environment parity

- incident runbooks

## 3. Security and compliance

The TRD includes token rotation, RBAC, TLS, encrypted PII, malware scanning, OWASP review, dependency scanning, and pen testing.

### Continuous tasks

- validation and auth audits

- dependency patching within SLA

- OWASP checks before phase launches

- role access reviews

- file upload security checks

- data retention / account deletion compliance

- pen test before Phase 3

## 4. Product analytics

### Continuous tasks

- define event naming standards

- funnel dashboards

- marketplace health metrics

- seller conversion metrics

- fraud reporting metrics

- monetization metrics

- retention metrics

# Milestones summary

## Milestone 1 — End of Week 2

Planning complete, architecture ready, repos and environments ready.

## Milestone 2 — End of Week 14

MVP complete:

- auth

- profiles

- categories

- listing CRUD

- search MVP

- chat

- admin moderation

- web + mobile usable

## Milestone 3 — End of Week 26

Growth beta complete:

- Elasticsearch

- maps

- advanced filters

- Cloudinary

- AI moderation v1

- saved searches

- push notifications

## Milestone 4 — End of Week 38

Revenue systems complete:

- payments

- subscriptions

- boosts

- lead credits

- analytics

- WhatsApp alerts

## Milestone 5 — End of Week 52

Advanced scale/intelligence complete:

- AI pricing

- KYC Level 2

- escrow

- virtual tours

- multilingual

- full trust layer

# Important dependencies and critical path

These are the tasks that can delay the whole project if not done on time:

## Critical path

- Architecture + API contracts

- Auth + user + listing services

- Category schema system

- Media upload pipeline

- Chat infrastructure

- Search migration to Elasticsearch

- Payment service and webhooks

- KYC provider integration

- Escrow compliance and payout flows

## Highest-risk items

- Elasticsearch + CDC pipeline

- payment webhooks and reconciliation

- AI moderation false positives/negatives

- KYC provider integration delays

- escrow/dispute workflow complexity

- mobile push notification reliability

- multilingual + RTL consistency